## V1_2023-10-27
Checklist | Date | Job-ID/CFAS | State | City | Type | Iteration | Section | Sl.No | Item | Description | Check | Reviewer-Note | Score-(%) | Submitted-By | Remarks
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | MQMS | 1.1 | Job Assignment | Check and Verify Your MQMS for the Job Assignment from your respective Supervisor | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | MQMS | 1.2 | MQMS -Job/Project Information | Check and Verify all Job/Project related information in PRISM matches with MQMS.(Field to be verified are Job/Business name, Job ID, Job address, Hub Name, Node Name, Job/Construction Type) If it doesn't match we need to prepare a Query document and send it to QG Design Supervisor/PMO and seek clarification | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | MQMS | 1.3 | Coax-Modules | Check and Verify all MQMS modules are as per assigned Job type (Coax). (Modules for Coax Jobs: ROUTE, COAX, PACKAGE PREP, QC) If the modules are Mismatch with assigned job type, then need we need to request the missing module from MQMS. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | MQMS | 1.4 | Fiber- Modules | Check and Verify all MQMS modules are as per assigned job type (Fiber). (Modules for Fiber Jobs: ROUTE, FIBER, PACKAGE PREP, QC) If the modules are mismatch with assigned job type, then need we need to request the missing module from MQMS. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | MQMS | 1.5 | Coax+Fiber-Modules | Check and Verify all MQMS modules are as per assigned job type (Coax-Fiber). (Modules for Fiber Jobs: ROUTE, COAX, FIBER, PACKAGE PREP, QC) If the modules are mismatch with assigned job type, then need we need to request the missing module from MQMS. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | MQMS | 1.6 | Timer | Ensure to start the timer, while creating the assigned job in Magellan. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | MQMS | 1.7 | Timer | If the job is been rejected for any reason then, we need to run the time for few minutes and then pause the timer. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | MQMS | 1.8 | Route Module | Ensure to run the timer in route module till modifications are done for support and addresses in Magellan | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | MQMS | 1.9 | Route Module | Aerial and UG lengths must always be updated as "0" in Route module in MQMS. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | MQMS | 1.10 | Route Module | Ensure to submit the route module in MQMS after the modifications are done for support and addresses in Magellan | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | MQMS | 1.11 | Coax Module | Post completion of Route Module, timer must run in Coax Module until the job is ready for submission to Internal QC. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | MQMS | 1.12 | Coax Module | Timer must be Paused once Coax-Module is completed and the Job is ready for submission for Internal QC. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | MQMS | 1.13 | Coax Module | Coax Module must not be submitted to Package Prep Module on MQMS. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | PRISM | 2.1 | Project Status | Project status in the survey tab must be "ACTIVATED" for all as-builts jobs. Project status in the survey tab must be "CANCELLED" for all Restore jobs. If it doesn't match we need to prepare a Query document and send it to QG Design Supervisor/PMO and seek clarification | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | PRISM | 2.2 | Secondary External PID | Ensure Secondary External PID in MQMS matches with the Design Number in Design tab on PRISM. (If it doesn't match then we must check for the PID in the design number drop down list and select the same for our respective job) If it the respective Secondary external PID is not there in the list then we need to prepare a query document and send it QG PMO and seek clarification. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | PRISM | 2.3 | Data Operations Name | We must input "Lopez, Robert V - p2728875" name in the Data Operations field on PRISM under Design Tab. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | PRISM | 2.4 | Design Received | Once the Data Operations field is populated with the respective name (as mentioned above) we must click the "Design Received" button in the Design tab. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | PRISM | 2.5 | Designer Name | Please input the respective QuadGen designer name from in the Designer Name field in Design Tab. Ensure this name must match with the name on MQMS. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | PRISM | 2.6 | Assign Designer | Once the Designer Name is populated, user must click on "Assign Designer" Button in Design Tab. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Input Validation | 3.1 | Input Files | On PRISM User must navigate to Documents Tab, Survey document section and download the file which will has name as "Asbuilt" and the attachment type must be "As-built". Please note: The file must have the latest date in the added date section with same attachment type. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Input Validation | 3.2 | Input Files | Look and download the files named as "Asbuilt" with attachment type as "Asbuilt" in the Production Report document section. Please note: The file must have the latest date in the added date section with same attachment type. This Check point is no more applicable. Please esnure you select NA for the same. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Input Validation | 3.3 | Input Files | If there is no input file present at either locations, the please prepare Query document and reach out to QG Design Supervisor/PMO and seek clarifications. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Input Validation | 3.4 | Input Files | Downloaded inputs files are legible, readable and clear to understand. If the files are corrupted and unable to understand, then prepare a Query Document and reach out to QG Design Supervisor/PMO and seek clarifications. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Input Validation | 3.5 | Inputs Comments | Please verify and ensure that Comments mentioned in PRISM Design tab must be Inline with the associated SOW. If it doesn't match we need to prepare a query document and send it to QG Design Supervisor/PMO and seek clarification. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Input Validation | 3.6 | AutoCAD Validation | If the Asbuilt input file is an export from AutoCAD tool and contains AutoCAD symbols then we need to follow the flow chart as mentioned in the reference document. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Input Validation | 3.7 | Restore Jobs Input files | We have to review all Design Deliverables as Inputs for Restore Jobs IF DESIGN DELIVERABLES ARE NOT PRESENT THEN WE MUST PREPARE QUERY DOCUMENT AND REACH OUT TO QG PMO AND SEEK CLARIFICATION. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Before Print | 4.1 | Fiber Layer | Ensure Fiber Layer is Unchecked before taking the export for Before Print file. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Before Print | 4.2 | Boundary | Ensure PRISM ID and PRISM PCAB layers option are selected in the Boundary Section in Layers tool on Magellan. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Before Print | 4.3 | Base Layers | When running a PDF report without the required layers on the system will ask you about it, all that is needed is to select the “include” button. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Before Print | 4.4 | Verification with Design | Before print Magellan data must match with the latest Design file. If it doesn't match we need to prepare a Query document and send it to QG Design Supervisor/PMO and seek clarification | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Before Print | 4.5 | Before Print | Prints must be taken by ensuring the asbuilt area is in the center of the page with all street names layers. Generate the PDF with the help of Lasso Tool only, | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Before Print | 4.6 | Naming Terminology | Prints must be extracted from Magellan before starting the asbuilt work & must be saved as per Standard naming terminology at the respective location on the network drive. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Before Print | 4.7 | Paper Type | While extracting the prints from Magellan, paper type must be selected as "ANSI E" from the drop down. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Before Print | 4.8 | STAMP | Screenshot of Design Tab (STAMP) must be taken from PRISM and pasted on the Before Print pdf at the top right or top left. Please note Screenshot must cover till the Design Number. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Before Print | 4.9 | Call Out properties | Check and Verify all the Callout Box (Title Block) properties are as per the Project Specification/Standards. Rectangle Box with Red Borders & yellow Fill, Text Font: Arial Narrow, BOLD & Text Size: 36. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Before Print | 4.10 | Title Block | Check and Verify the Title Block which has below information is placed in the Before Print on 1st page right below the STAMP. Title Block: Node Name, Instance, Map coordinates, & BEFORE PRINT. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.1 | Job Creation | Job created on Magellan must have Job Name, description and Region as mentioned below. Job Name: MNS_Prism ID_01 Description (Asbuilt Jobs): Coax Asbuilt, Description (Restore Jobs): Coax Restore Region: As per Prism/MQMS If the wrong region is selected then we need to delete the job and recreate it again. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.2 | Catalogs | Ensure any new changes in Support Structures or Coax elements must be built in the same catalogues as per existing data catalogue. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.3 | Changes verification | Asbuilt Jobs - Visually inspect & Verify all changes/modifications are done in Magellan as per the given SOW and Inputs. Restore Jobs - All support and Coax elements build state of the respective area of Interest must be changed to NOT BUILT by disconnecting the respective area of interest except for downstream affected network. Affected downstream network must match with Before Design Print. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.4 | Address Validation | All address and the LU type must be matching with PRISM and MQMS. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.5 | Support Structures | Support structures must be selected & placed as per the latest and standard guidelines. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.6 | Coax Elements | All Coax elements must be selected & placed as per the latest and standard guidelines. Additionally please refer section 7.1 of design spec for area specific guidelines | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.7 | Coax Elements | Relink all the coax elements to Existing Support elements and length should match as per strand/trench Length in Magellan. Check this point even if Built as Designed job also. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.8 | Coax Elements | Verify all the COAX Equipments (Splitters, taps, Actives etc) should match with SOW. Check this point even if Built as Designed job also. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.9 | Build State | Asbuilt Jobs: The build state must be "Asbuilt" of all the address, support structures, Coax Elements updated or changed as per the SOW inside the respective PRSIM PCAB Boundary It must be Always "Asbuilt" even added any new Elements of COAX, Support and Addresses. Restore Jobs: Built state Must be "NOT BUILT" | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.10 | Boundary Type | Asbuilt Jobs: Existing PRISM ID Boundary type must be changed to "PRSIM PCAB Boundary" & renamed with JOB ID, thru inspector tool. Restore Jobs: Existing PRISM ID Boundary type must be changed to "NOT BUILT Boundary" & renamed with JOB ID, thru inspector tool. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.11 | Boundary Data | Asbuilt Jobs: Ensure entire area mentioned in the SOW falls under "PRSIM PCAB Boundary" Restore Jobs: Ensure entire area of interest wherein the built state is changed to NOT BUILT must falls under "NOT BUILT Boundary" | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.12 | Boundary Placement | Asbuilt jobs: If existing PRISM ID Boundary not available in Magellan, then New "PRSIM PCAB Boundary" must be placed according to the parcels in Magellan. Restore jobs: If existing PRISM ID Boundary not available in Magellan, then New "NOT BUILT Boundary" must be placed according to the parcels in Magellan. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.13 | Boundary Placement | If our SOW involves working near to any tap location then our Boundary must cover all the LU's parcels been served by the respective tap by enabling parcel layer. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.14 | Boundary Placement | Make sure that none of the COAX/FIBER - cables/elements must overlap the boundary Note: When working on coax, make sure to turn back off the fiber layer after verifying for overlaps. | No | ewfwef | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.15 | Trace & Run Analyze tool | Ensure to Run the Trace and Analyze Tool from previous active with Tap Prediction OFF after completion of asbuilt changes in Magellan. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.16 | Trace & Run Analyze tool | If the changes are done on the entire node Boundary then Trace & Analyze tool must be used from the respective Node. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.17 | Power Tool | Ensure to Run the Power Tool after completion of asbuilt changes in Magellan. This Point is applicable only if we are changing or updating any actives, else this point is NA. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.18 | Boundary flushing | Our new PRISM PCAB/NOT BUILT boundary must be flushed to other existing PCAB or Node Boundaries. There must not be any overlap between our boundaries and existing boundaries. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.19 | Shape & Position of all elements | All Support & Coaxial elements shape and position inside our PRISM PCAB boundary must match with provided Asbuilt input file. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.20 | Rotation of all elements | All Support & Coaxial elements rotations inside our PRISM PCAB boundary must follow standard Charter guidelines. Please review attached reference document for more information. (Especially DC Couplers, Amplifiers and Splitters must be rotated according to the design specific standard guidelines) | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.21 | AutoCAD Input file drafting | Identify all support & coax elements AutoCAD symbols from the reference document and ensure same type of element is chosen and drafted on Magellan. Please note: This point is only applicable when ACAD data is available on Magellan. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.22 | Manufacture types | All coaxial elements manufactures types must match with regional specification document which is available on the MQMS Library. Additionally please refer section 7.1 of design spec for area specific guidelines | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.23 | Base Layers | Ensure 3 Base layers, Centre line, Parcel line and Street Names are enabled. If any of these are missing, please turn on Misc layers | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Magellan Tool | 5.24 | Scaling | Match the scaling of all devices in the area. (1.5 scale when working in TWGBO for coax) | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | After Deliverables | 6.1 | After Print extraction | Prints must be exported by ensuring the asbuilt area is in the center of the page with all street names layers. Generate the PDF with the help of Lasso Tool only. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | After Deliverables | 6.2 | Zoom Level | Zoom level must be same as Before Print. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | After Deliverables | 6.3 | Paper Type | While extracting the prints from Magellan, paper size type must be selected as "ANSI E" from the drop down. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | After Deliverables | 6.4 | STAMP | Screenshot of Design Tab (STAMP) must be taken from PRISM and pasted on the After Print pdf at the top right or top left. Please note Screenshot must cover till the Design Number. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | After Deliverables | 6.5 | Title Block | Check and Verify the Title Block which has below information is placed in the After Print on 1st page right below the STAMP. It must be clear and legible. Title Block: Node Name, Instance, MAP & AFTER PRINT. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | After Deliverables | 6.6 | Comment Call Out | Check and Verify the asbuilt comment call out should always be as mentioned below. If any asbuilt changes are done then comment should be "UPDATED PER ASBUILT" and if No changes are done then comments should be "BUILT AS DESIGNED" No detailed description is needed on after print. Check and Verify the Restore comment call out should always be as mentioned below. For restore jobs comment should be "RESTORED" | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | After Deliverables | 6.7 | Call Out properties | Check and Verify all the Callout Box (Title Block & Comment Callout) properties are as per the Project Specification/Standards. Rectangle Box with Red Borders & yellow Fill, Text Font: Arial Narrow, BOLD & Text Size: 36. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | After Deliverables | 6.8 | Report | Extract the BOM report with Coax all and Support all selected from Drop down list in the BOM type list. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | After Deliverables | 6.9 | House counts & address | Respective House counts and address inside PRISM PCAB boundary must be present and visible on the After PDF document which must match the data on the Magellan. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | After Deliverables | 6.10 | Base Layers | When running a PDF report without the required layers on the system will ask you about it, all that is needed is to select the “include” button. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Deliverables Naming Format, Final Folder format & contents | 7.1 | Before Print | Before Print Naming should be as per below Naming standard. PRISM ID_BUSINESS NAME_BEFORE_COAX THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Deliverables Naming Format, Final Folder format & contents | 7.2 | After Print | After Print Naming should be as per below Naming standard. PRISM ID_BUSINESS NAME_AFTER_COAX THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Deliverables Naming Format, Final Folder format & contents | 7.3 | BOM Folder | BOM folder extracted from Magellan must be renamed as below. PRISM ID_BUSINESS NAME_AFTER_BOM | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Deliverables Naming Format, Final Folder format & contents | 7.4 | Final Folder Contents | Final Folder must contains Following deliverables. BEFORE PRINT & AFTER PRINT THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Deliverables Naming Format, Final Folder format & contents | 7.5 | Final Package Naming | Asbuilt Jobs: Final Folder Naming should be as per below Naming standard. (PRISM ID)_FINAL_ASBUILT_(COAX) Restore Jobs: Final Folder Naming should be as per below Naming standard. (PRISM ID)_FINAL_RESTORE_(COAX) | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.1 | Final Package Upload | Upload the Final Package folder in PRISM under Documents tab. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.2 | Final Package Upload | Ensure the Title name on "Add Document" pop must be same as per the Final Package file name. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.3 | Final Package Upload | Ensure the Attachment type on "Add Document" pop must be selected as "IP-Issue Print" from the drop down menu. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.4 | Footages on PRISM | Asbuilt Jobs: Based on the environment type (Aerial/UG) footages must be updated only on the Design Coax section in Design Tab in PRISM. For Aerial it must be updated under "Aerial Footage" & "Aerial Overlash" fields and for UG it must be updated under "UG Footage" field. Restore Jobs: Aerial/UG/Overlash/Rework & Removed footages must be "0" on PRISM | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.5 | Footages on PRISM | Above updated footages must match with SOW and BOM. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.6 | Footages on PRISM | Asbuilt Jobs: Based on the environment type (Aerial/UG) footages must be updated only on the asbuilt section in Asbuilt Tab in PRISM. For Aerial it must be updated under "Aerial Footage" & "Aerial Overlash" fields and for UG it must be updated under "UG Footage" field. Restore Jobs: Aerial/UG/Overlash/Rework & Removed footages must be "0" on PRISM | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.7 | Footages on PRISM | Above updated footages must match with Design tab | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.8 | Workspace on MQMS | Workspace name must be same as the Job ID created on Magellan (Refer 5.1) THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.9 | Merge Ticket on MQMS | "MAGELLAN" must be mentioned in Merge Ticket option in MQMS THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.10 | Footages on MQMS | Asbuilt Jobs: Update same footages at the respective fields matching with PRISM as mentioned in above checkpoints. Rest other footage sections must be marked as "0" Restore Jobs: Aerial/UG/Overlash/Rework & Removed footages must be "0" on MQMS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.11 | Add Node on MQMS | This option must be selected as "No" for all As-builts jobs. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.12 | EST HH Passed Aerial/UG on MQMS | These fields must match with PRISM | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.13 | Submission Coax Module | Job must be submitted to Package Prep module on MQMS THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.14 | Timer On Package Prep | Run timer in Package Prep Module THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.15 | Submit Design in PRISM | Verify all the footages are correct and click on "Design Ready for QC" button THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.16 | Submit Package Prep in MQMS | QC option is selected while submitting the PACKAGE PREP module in MQMS. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.17 | Merge Job | Job is Merged on Magellan Tool after verification. THIS IS APPLICABLE FOR ASBUILT AND RESTORE JOBS | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.18 | Design Frequency in PRISM | Design frequency on PRISM (Design TAB) must match with the Highest frequency of equipment in Magellan. If Highest frequency present on Magellan is not available in the list of PRISM, then we must take the next available frequency. | Yes |  | 98.9 | Ajith V
BAU-ABD-COAX | 2023-10-27 16:45:56 | 1168043 | AZ | ZR | Self QC | 1 | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | 8.19 | Scaling | Match the scaling of all devices in the area. (1.5 scale when working in TWGBO for coax) | Yes |  | 98.9 | Ajith V