## V1_2023-10-04
Checklist | Date | Job-ID/CFAS | State | City | Type | Iteration | Remarks | Section | Item | Description | Check | Reviewer-Note | Score-(%) | Submitted-By
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | MQMS | Job Assignment | Check and Verify Your MQMS for the Job Assignment from your respective Supervisor | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | MQMS | MQMS -Job/Project Information | Check and Verify all Job/Project related information in PRISM matches with MQMS. (Fields to be verified - Secondary Design Number,Job/Business name, Job ID, Job address, Hub Name, Node Name, Job/Construction Type) If it doesn't match, we need to prepare a Query document and send it to QG Design Supervisor/PMO and seek clarification | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | MQMS | SOW | Ensure the job is related to FC+ (COAX_FIBER) or FIA (Fiber Only) job before starting the job. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | MQMS | Fiber Module | Check and Verify all MQMS modules are as per assigned job type (Fiber Only - FIA). (Modules for Fiber Jobs: ROUTE, FIBER, PACKAGE PREP, QC) If the modules are mismatch with assigned job type, then need we need to request the missing module from MQMS. If the modules mismatch with assigned job type, raise a request for the missing module from MQMS. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | MQMS | Coax+Fiber Modules | Check and Verify all MQMS modules are as per assigned job type (Coax-Fiber - FC+). (Modules for Fiber Jobs: ROUTE, COAX, FIBER, PACKAGE PREP, QC) If the modules mismatch with assigned job type, raise a request for the missing module from MQMS. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | MQMS | Timer | Ensure to start the timer, while creating the assigned job in Magellan. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | MQMS | Timer | If the job is being rejected back to customer for any reason make sure to record time (a few minutes) on MQMS | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | MQMS | Route Module | Aerial and UG lengths must always be updated as "0" in Route module in MQMS. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | MQMS | Route Module | Ensure to submit the route module in MQMS after the modifications are done for support and addresses in Magellan, post which timer must be started on respective module | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | MQMS | Coax + Fiber Module | Post completion of Route Module, timer must run in Fiber Module until the job is ready for submission to Internal QC. (Applicable Fiber only jobs) Post completion of Route Module, Submit the COAX Module and run the timer in Fiber module until the job is ready for submission to Internal QC. (Applicable for COAX-Fiber jobs) | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | MQMS | Fiber Module | Fiber Module must not be submitted to Package Prep Module on MQMS untill IQC is completed. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | PRISM | Project Status | Project status in the survey tab must be "ACTIVATED" for all as-builts jobs. Project status in the survey tab must be "CANCELLED" for all Restore jobs. If it doesn't match we need to prepare a Query document and send it to QG Design Supervisor/PMO and seek clarification | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | PRISM | Data Operations Name | We must update "Lopez, Robert V - p2728875" name in the Data Operations field on PRISM under Design Tab. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | PRISM | Design Received | Once the Data Operations field is populated with the respective name (as mentioned above) we must click the "Design Received" button in the Design tab. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | PRISM | Designer Name | Please input the respective QuadGen designer name from in the Designer Name field in Design Tab. Ensure this name must match with the name on MQMS. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | PRISM | Assign Designer | Once the Designer Name is populated, user must click on "Assign Designer" Button in Design Tab. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Input Validation | Input Files | On PRISM User must navigate to Documents Tab, Survey document section and download the file which will has name as "Asbuilt" and the attachment type must be "As-built". "Please note: The file must be of latest date with ASBUILT attachment type. If there is no Asbuilt file under survey document section, reach out to your supervisor for confirmation on rejecting the job." | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Input Validation | Input Files | Downloaded inputs files are legible, readable and clear to understand. If the files are corrupted and unable to understand, then prepare a Query Document and reach out to QG Design Supervisor/PMO and seek clarifications. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Input Validation | Input Files | Please verify and Ensure the Fiber information is available or not. (Fiber information: Hub Info, Tie point, Mux info etc.) IF AUDIT/SPLICING SHEET is not available please reject the job | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Input Validation | Inputs Comments | Please verify and ensure that Comments mentioned in PRISM Design tab must be Inline with the associated SOW. If it doesn't match we need to prepare a query document and send it to QG Design Supervisor/PMO and seek clarification. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Input Validation | AutoCAD Validation | If the Asbuilt input file is an export from AutoCAD tool and contains AutoCAD symbols then we need to follow the flow chart as mentioned in the reference document. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Input Validation | Restore Jobs Input files | We have to review all Design Deliverables as Inputs for Restore Jobs If it doesn't match we need to prepare a query document and send it to QG Design Supervisor/PMO and seek clarification. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Before Print | Layers | Ensure Coax Layer is Unchecked before taking the export for Before Print file for all FIA (Fiber only) Jobs. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Before Print | Layers | Ensure both Coax and Fiber Layers are ON, if the job is related to FC+ (COAX-FIBER) before taking the export for Before Print file. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Before Print | Boundary | Ensure PRISM ID and PRISM PCAB layers option are selected in the Boundary Section in Layers tool on Magellan. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Before Print | Base Layers | When running a PDF report without the required layers on the system will ask you about it, all that is needed is to select the “include” button. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Before Print | Design Verification | Before print Magellan data must match with the latest Design file. If it doesn't match we need to prepare a Query document and send it to QG Design Supervisor/PMO and seek clarification | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Before Print | Before Print | Prints must be taken by ensuring the asbuilt area is in the center of the page with all street names layers. Generate the PDF with the help of Lasso Tool only, | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Before Print | Naming Terminology | Prints must be extracted from Magellan before starting the asbuilt work & must be saved as per Standard naming terminology at the respective location on the network drive. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Before Print | Paper Type | While extracting the prints from Magellan, paper type must be selected as "ANSI E" from the drop down. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Before Print | STAMP | Screenshot of Design Tab (STAMP) must be taken from PRISM and pasted on the Before Print pdf at the top right or top left. Please note Screenshot must cover till the Design Number. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Before Print | Call Out properties | Check and Verify all the Callout Box (Title Block) properties are as per the Project Specification/Standards. Rectangle Box with Red Borders & yellow Fill, Text Font: Arial Narrow, BOLD & Text Size: 36. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Before Print | Title Block | Check and Verify the Title Block which has below information is placed in the Before Print on 1st page right below the STAMP. Title Block: Node Name, Instance, Map coordinates, & BEFORE PRINT. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Job Creation | Job created on Magellan must have Job Name, description and Region as mentioned below. Job Name: MNS_Prism ID_01 Description (Asbuilt Jobs): Fiber Asbuilt, Description (Restore Jobs): Fiber Restore Region: As per Prism/MQMS If the wrong region is selected then we need to delete the job and recreate it again. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Catalogs | Ensure any new changes in Support Structures, Coax, Fiber elements must be built in the same catalogues as per existing data catalogue. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Changes verification | Asbuilt Jobs - Visually inspect & verify all changes/modifications are done in Magellan as per the given SOW and Inputs. Restore Jobs - All support and Fiber elements build state of the respective area of Interest must be changed to NOT BUILT by disconnecting the respective area of interest. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Address Validation | All address and the LU type must be matching with PRISM and MQMS. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Support Structures | All Support structures must be selected & placed as per the latest and standard guidelines. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Fiber Elements | All Fiber elements must be selected & placed as per the latest and standard guidelines. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Fiber Elements | Ensure Mux Type, range and Reserved Wavelengths are match as per Fiber information provided in PRISM and Input files. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Fiber Elements | Fiber splicing/Connectivity must match as per the splicing docs. (Splice matrix, OTDR report, Cus sheets etc. provided in PRISM) | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Fiber Elements Naming | Naming of the Fiber elements must be as per the latest and standard guidelines. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Linking | Relink all the Fiber elements to Existing Support elements and length should match as per strand/trench Length in Magellan. Check this point even if Built as Designed job also. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Linking | Ensure the Address is linked to Fiber Termination box (Business class) for both Forward and Return. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Verification of Design | Verify all the Fiber Elements (Cable Size, Splitters/Muxes, Splice cases, Business class devices) should match with SOW. Check this point even if Built as Designed job also. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Fiber Elements Naming | Ensure the Naming of Termination box (Business class) must be "BC-customer address without spaces". Example: BC-29804LAKESHOREBLVD | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Circuits & Sub circuits | Ensure to Create Circuits and Sub-circuits for reserved Wavelengths in the MUX. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Naming Circuits & Sub circuits | Ensure the naming of Circuits and Sub-circuits as per the standards. Circuit naming format: BC-customer address without spaces Subcircuits naming format: BC-customer address without spaces_FWD/RTN | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | BUILD STATE | Asbuilt Jobs: The build state must be "Asbuilt" of all the address, support structures, Fiber(alos coax if hybrid) Elements updated or changed as per the SOW inside the respective PRSIM PCAB Boundary It must be Always "Asbuilt" even added any new Elements of FIBER, Support and Addresses. Restore Jobs: Built state Must be "NOT BUILT" | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Boundary Placement | Asbuilt Jobs: Existing PRISM ID Boundary type must be changed to "PRSIM PCAB Boundary" & renamed with JOB ID, thru inspector tool. Restore Jobs: Existing PRISM ID Boundary type must be changed to "NOT BUILT Boundary" & renamed with JOB ID, thru inspector tool. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Boundary Placement | Asbuilt jobs: If existing PRISM ID Boundary not available in Magellan, then New "PRSIM PCAB Boundary" must be placed according to the parcels in Magellan. Restore jobs: If existing PRISM ID Boundary not available in Magellan, then New "NOT BUILT Boundary" must be placed according to the parcels in Magellan. Ensure entire area mentioned in the SOW falls under our Boundary" | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Boundary Placement | If our SOW involves working near to any Termination box (Business class) then our Boundary must cover all the LU's parcels been served by the respective tap by enabling parcel layer. Note : All Boundaries must be flushed & made sure turned off COAX/Fiber layers doesn't overlap the PCAB boundary. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Trace & Analyze | Ensure to Run the Trace from given MUX by selecting splice matrix TOOL in Inspector panel. Customer connected Fibers must be trace back to Headend/hub. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Shape & Position of all elements | All Support & Fiber elements shape/positioning/rotation inside our PRISM PCAB boundary must match with provided Asbuilt input file & also follow standard Charter guidelines. If there is a conflict between guideline & asbuilt reach out to your respective supervisor | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Manufacture types | All Fiber elements manufacturer types must match with regional specification document which is available on the MQMS Library. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Base Layers | Ensure 3 Base layers - Centre line, Parcel line and Street Names are enabled. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Magellan Tool | Scaling | Match the scaling of all devices in the area. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | After Deliverables | After Print extraction | Prints must be exported by ensuring the asbuilt area is in the center of the page with all street names layers. Generate the PDF with the help of Lasso Tool only. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | After Deliverables | Zoom Level | Zoom level must be same as Before Print. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | After Deliverables | Paper Type | While extracting the prints from Magellan, paper size type must be selected as "ANSI E" from the drop down. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | After Deliverables | STAMP | Screenshot of Design Tab (STAMP) must be taken from PRISM and pasted on the After Print pdf at the top right or top left. Please note Screenshot must cover till the Design Number. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | After Deliverables | Title Block | Check and Verify the Title Block which has below information is placed in the After Print on 1st page right below the STAMP. It must be clear and legible. Title Block: Node Name, Instance, MAP & AFTER PRINT. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | After Deliverables | Comment Call Out | Check and Verify the asbuilt comment call out should always be as mentioned below. If any asbuilt changes are done then comment should be "UPDATED PER ASBUILT" and if No changes are done then comments should be "BUILT AS DESIGNED" No detailed description is needed on after print. Check and Verify the Restore comment call out should always be as mentioned below. For restore jobs comment should be "RESTORED" | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | After Deliverables | Call Out properties | Check and Verify all the Callout Box (Title Block & Comment Callout) properties are as per the Project Specification/Standards. Rectangle Box with Red Borders & yellow Fill, Text Font: Arial Narrow, BOLD & Text Size: 36. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | After Deliverables | Report | Extract the BOM report with respective layers selected from Drop down list in the BOM type list. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | After Deliverables | House counts & address | Respective House counts and address inside PRISM PCAB boundary must be present and visible on the After PDF document which must match the data on the Magellan. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | After Deliverables | Base Layers | "Ensure all the required layers are turned on before generating a PDF Note: Select ""Include"" option if the system prompts while generating a pdf." | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Deliverables Naming Format, Final Folder format & contents | After Print | After Print Naming should be as per below Naming standard. PRISM ID_BUSINESS NAME_AFTER_FIBER Hybrid jobs need 2 separate packages (1 for COAX & 1 for Fiber) | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Deliverables Naming Format, Final Folder format & contents | BOM Folder | BOM folder extracted from Magellan must be renamed as below. PRISM ID_BUSINESS NAME_AFTER_BOM | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Deliverables Naming Format, Final Folder format & contents | Final Folder Contents | Final Folder must contains Following deliverables. BEFORE PRINT & AFTER PRINT | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Deliverables Naming Format, Final Folder format & contents | Final Package Naming | Asbuilt Jobs: Final Folder Naming should be as per below Naming standard. (PRISM ID)_FINAL_ASBUILT_(FIBER) Hybrid jobs need 2 separate packages Restore Jobs: Final Folder Naming should be as per below Naming standard. (PRISM ID)_FINAL_RESTORE_(FIBER) | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Final Package Upload | Ensure the Title name on "Add Document" pop must be same as per the Final Package file name. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Final Package Upload | Ensure the Attachment type on "Add Document" pop must be selected as "IP-Issue Print" from the drop down menu. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Footages on PRISM | Asbuilt Jobs: Based on the environment type (Aerial/UG) footages must be updated only on the Design Fiber section in Design Tab in PRISM. For Aerial it must be updated under "Aerial Footage" & "Aerial Overlash" fields and for UG it must be updated under "UG Footage" field. Restore Jobs: Aerial/UG/Overlash/Rework & Removed footages must be "0" on PRISM | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Footages on PRISM | Above updated footages must match with SOW and BOM. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Footages on PRISM | Asbuilt Jobs: Based on the environment type (Aerial/UG) footages must be updated only on the Construction Fiber asbuilt section in Asbuilt Tab in PRISM. For Aerial it must be updated under "Aerial Footage" & "Aerial Overlash" fields and for UG it must be updated under "UG Footage" field. Restore Jobs: Aerial/UG/Overlash/Rework & Removed footages must be "0" on PRISM | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Footages on PRISM | Above updated footages must match with Design tab | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Workspace on MQMS | Workspace name must be same as the Job ID created on Magellan (Refer 5.1) | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Merge Ticket on MQMS | "MAGELLAN" must be mentioned in Merge Ticket option in MQMS | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Footages on MQMS | Asbuilt Jobs: Update same footages at the respective fields matching with PRISM as mentioned in above checkpoints. Rest other footage sections must be marked as "0" Restore Jobs: Aerial/UG/Overlash/Rework & Removed footages must be "0" on MQMS | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Add Node on MQMS | This option must be selected as "No" for all As-builts jobs. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | EST HH Passed Aerial/UG on MQMS | These fields must match with PRISM | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Module Submission | Job must be submitted to Package Prep module on MQMS | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Timer On Package Prep | Run timer in Package Prep Module | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Submit Design in PRISM | Verify all the footages are correct and click on "Design Ready for QC" button | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Submit Package Prep in MQMS | QC option is selected while submitting the PACKAGE PREP module in MQMS. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Merge Job | Job is Merged on Magellan Tool after verification. | Yes |  | 100.0 | Shrikant Sriramulu Bomma
Testing ATX AS-Built | 2023-10-04 12:07:26 | 4624900 | TX | WACO | Self QC | 1 |  | Final Job submission on MQMS and PRISM (Applicable for only Internal QC Team) | Design Frequency in PRISM | Applicable only for hybrid jobs Design frequency on PRISM (Design TAB) must match with the Highest frequency of equipment in Magellan. If Highest frequency present on Magellan is not available in the list of PRISM, then we must take the next available frequency. | Yes |  | 100.0 | Shrikant Sriramulu Bomma